## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/07- 09/21 | 1. Roles assigned 2. Setup github 3. Finalized project idea 4. Determing the devalopment tool which we will use 5. Bulid Initial Algorithm plan 6. Make the Logo of our project | N/A | N/A | In progress | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Shawn
Dawei
Siming
Lijian
Haiyang

## Shawn Hu
Your Lead Roles: Team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 9 | 7 | 2 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 2 | 0.5 | 1.Bulid initial plan of project 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. | 1. finish Algorithm in 2 weeks, be able to create simple words like hello world project next week 2. Send task assignments to all members again | 0 - continue to learn JavaScript 1 - continue to define requirements 2 - finish Algorithm design | 15
2 | 09/15-09/21 | 15.5 | 12.5 | 3 | 0 - frontend skill learning 1 - Organize tables and plan different schedules 2 - reading literatures and design project algorithm 5 - Make the final decision of each role and assign task. 7 - make ppt for Iteration0 presetation | 3 | 1 | 6 |  |  | 0.5 |  | 2 | 1.Bulid initial Algorithm and make the Flowchart of Algorithm 2. Submit Iteration 0 on git 3. Participate in Iteration 0 presentation 4. Organize meeting documents and set next meeting zoom room 5. Make the final decision of each leader role 6. Make the Group logo | 1.Due to the late selection of the project topic, the algorithm and framework have been designed, but we still need consider about algorithm detail 2. reassign the leader role for team work | 1. finish Algorithm in 1 weeks, be able to create simple words like hello world project next week 2. Send task assignments to all members again | 0 - continue to learn JavaScript 1 - continue to finsih algorithm design 2 - implement a basic hello world on framework | 20

## Dawei Yin
Your Lead Roles: Design & Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 10 | 8 | 2 | 0 - pick up java and its frameworks 1 - define high level requirements, 5 - make project plan 6 - set up git 7 - research similar algorithms | 3 | 1 |  | 0 | 0 | 1 | 2 | 1 | 1.Bulid initial plan of project 2. Set up git, commit a test message on git | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. | 1. finish Algorithm in 2 weeks, be able to create simple words like hello world project next week 2. Send task assignments to all members again | 0 - continue to design algorithm for the project 1 - continue to define requirements 3 - implement a basic hello world on framework | 10
2 | 09/15-09/21 | 16.5 | 13.5 | 3 | 0 - read the research papers 1 - analysis the requirement for the iGroup project 2 - try to come up a valid algorithm for this project 5 - commute with professor and document the requirements 6 - set up java development environment | 3 | 2 | 4 | 0 | 0 | 1.5 | 1 | 2 | 1. gather the info for the project requirements from the instructor 2. set up development environment 3. keep working on the algorithm | 1. it might take more time on designing valid algorithm than we expected for this project | 1. set a deadline on designing the algorithm, if we cannot make it, we might consider to change our project proposal. | 1. come up a valid algorithm 2. design the architecture for the implementation of this algorithm | 15

## Siming Qian
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 8.5 | 6.5 | 2 | 0 - pick up java front end 1 - define basic level requirements, 5 - set up meeting time, role distribution 6 - set up git 7 - research similar products, prepare presentation | 3 | 0.5 | 0 | 0 | 0 | 2 | 0 | 1 | 1. setting up git 2. role distribution | 1. having trouble find free time in common 2. late start on proj topic | 1. finsih the algorithm | 1. algorithm | 6.5
2 | 09/15-09/21 | 6 | 4 | 2 | 0 - java front end learning 1 - get yuting's request from dawei 5 - role distribution again due to a memeber left 7 - reading paper related to algorithm | 3 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 2 | 1. find the algorithm 2. presentation | 1. surprise from the pop due 2. finding the algorithm | 1. finish the algorithm | 1. algorithm 2. java front end | 6

## Lijian Yao
Your Lead Roles: Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 7 | 5 | 2 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 |  |  |  |  | 0.5 | 1 | 0.5 | 1.Set up git 2.Set up a team 3.communication plan 4.Meet teammates | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. | 1.Finishing up Algorithm within few week | 1. Learning 2. Finishing SPP doc 3.Prepare for Presentation | 7
2 | 09/14-09/21 | 7 | 5 | 2 | 0 - read several tutorials, choose the best tool to use for our team 5 - make project plan, received all the task assigned by team leader 6 - set up git, finishing up the SPPP doc 7 - Prepare presentation | 3 |  |  |  |  | 0.5 | 1 | 0.5 | 1.Finished SPPP doc 2.Prepare for presentation 3.Finishing up Algorithm | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. 3.We lost a Teammate so we had to fill in his role | 1.Finishing up Algorithm within few week | 1. Learning 2.Framework 3.Algorithm more TBD by next meeting | 7

## Haiyang Wang
Your Lead Roles: QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 8 | 6 | 2 | 0 - learn git, github, github desktop, 1 - define high level requirements, 5 - make project plan, send reminders to team members, 6 - set up git, 7 - research similar products, prepare presentation. | 3 | 1 | null | null | null | 0.5 | 1 | 0.5 | 1.Bulid initial plan of project 2. Set up git, commit a test message on git 3. Participate in Iteration 0 | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet, 2. communication is not clear. Task assignments is not clear. | 1. Communicate with teammates, frame design decided, 2. Task assignments successfully finished | 1. Reading References, 2. Finish Algorithum design | 6 - 12
2 | 09/15-09/21 | 10 | 7 | 3 | 0 - learn basic contents of testing, 1 - analysis the requirement for the iGroup project, 2 - reading literatures and design project algorithm, 5 - Make the final decision of each role together. 7- Finish sessions in SPPP, SPPP_RiskManagement | 3 | 1 | 3 | null | null | 0.5 | null | 2.5 | 1. Finish QA session in SPPP, finish testing and integration sessions in SPPP_RiskManagement, 2. Participate in Iteration 0 presentation | 1. Due to the late selection of the project topic, although the algorithm and framework have been designed, we still need consider about algorithm detail 2. leader role for team work is not clear | 1. finish Algorithm in 1 weeks, 2. Get the role, tasks finished | 1. Reading References, 2. Finish Algorithum design 3. Learn more about testing | 9 - 15