## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Personel | Loss team members | One or two more member drop the class | 4 | 3 | 3 | 18 | Team leader and all members | TBD | Redefine the project scope if necessary, and assign the tasks to other team members. | one member move to another team so far | Open
| add new team members | One member joined our team | 3 | 3 | 3 | 27 | Team leader and all members | TBD | Redefine the project scope if necessary, and assign the tasks to other team members. | No one joined our team so far | Open
| Lack of motivation or responsibility | Someone didn't pay attention on their own responsibility | 2 | 5 | 5 | 20 | Team leader and all members | TBD | Make Warming to people who is not pay atttention | Problem not appear yet | Open
Communication | duplicate work | Not clearify responsebility of each role | 2 | 4 | 4 | 32 | Team leader and all members | TBD | Make decision for each role | After two meetings we finaly decide each leader role | Open
| worked on wrong components | Delayed communication leads to inconsistent progress | 2 | 5 | 4 | 16 | Team leader and all members | TBD | Set more meetings | Problem not appear | Open
| useless work | Work conflict caused by lack of communication | 3 | 4 | 5 | 30 | Team leader and all members | TBD | Encourage more communication | Problem not appear | Open
| inconsistent work | No suitable algorithm was found | 4 | 2 | 5 | 40 | Team leader and all members | TBD | Read more literature and finalize the algorithm as soon as possible | Haven't decide Algorithm yet | Open
Requirements | unclear requirements | misunderstanding desired functions | 2 | 4 | 3 | 24 | Req leader | TBD | double check with Yuting and delivery it to the group members | Not yet | Open
| scope creep | more changes adding | 3 | 3 | 3 | 27 | Req leader and all members | TBD | keep structure simple or asking not adding unnecessary funcetions | Not yet | Open
| constant requirements changes | changes of desired basic function | 1 | 5 | 5 | 25 | Req leader and all members | TBD | reimplement functions | Not yet | Open
Management | improper task assignments | assign improper task to the team member | 1 | 5 | 5 | 25 | Team Leader and all members | TBD | discuss with all member and fix the problem | Problem not appear | Open
| improper planning | miss the deadline | 1 | 5 | 5 | 25 | Team Leader and all members | TBD | Make up all the stuff | Problem not appear | Open
| lack of management skills | fail to lead the team | 2 | 5 | 5 | 20 | Team Leader and all members | TBD | Ask team leader for help | Problem not appear | Open
Technology competence | Not familiar with the framework used | one or more team memebers are confused with the framework | 2 | 3 | 3 | 36 | Configuration leader and all memebers | TBD | Configuration leader help all memebers or help each others | Problem not appear yet | Open
| Not familiar with the programming language used | one or more team memebers are not familiar with the language we used | 1 | 3 | 3 | 45 | Configuration leader and all memebers | TBD | Configuration leader help all memebers or help each others | Problem not appear yet | Open
| Not familiar with unit testing | one or more team memebers are not familiar with testing | 2 | 3 | 3 | 36 | Configuration leader and all memebers | TBD | Configuration leader help all memebers or help each others | Problem not appear yet | Open
| Other technology incompetence | one or more team memebers are having technology diffculty | 2 | 3 | 3 | 36 | Configuration leader and all memebers | TBD | Configuration leader help all memebers or help each others | Problem not appear yet | Open
| Not familiar with Git | one or more team memebers are not familiar with Git | 1 | 3 | 3 | 45 | Configuration leader and all memebers | TBD | Configuration leader help all memebers or help each others | Problem not appear yet | Open
Design and implementation | Improper design | lack of moduality, and poor scalablity | 3 | 4 | 3 | 18 | Design and implementation leader | TBD | Refine project, add modurality | Not start yet | Open
| improper technology stack | bad performance or long develop period | 2 | 4 | 3 | 24 | Design and implementation leader and all members | TBD | change stack ASAP | Not start yet | Open
| Messy code | bad readability, potential human error | 3 | 2 | 4 | 48 | All members | TBD | Define coding convention | Not start yet | Open
Testing | Not enough testing | More Bugs, more dangerous situation | 3 | 3 | 3 | 27 | QA leader and all members | TBD | Add more tests. Find Bugs | Not start yet | Open
| Tests repeat | Bugs not detected. | 3 | 3 | 3 | 27 | QA leader and all members | TBD | Delete repeat tests. Add more tests | Not start yet | Open
Integration and deployment | Not enough time for integration and deployment | Parts cannot co-work. Errors detected. | 2 | 4 | 3 | 27 | QA leader and all members | TBD | Prepare for more time. Add more integration tests. | Not start yet | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.