## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/07- 09/21 | 1. Roles assigned 2. Setup github 3. Finalized project idea 4. Determing the devalopment tool which we will use 5. Bulid Initial Algorithm plan 6. Make the Logo of our project | N/A | N/A | In progress | NA | NA | NA | NA | NA | 104 | 74 | 30 | NA | NA | NA | NA | NA | NA | NA | NA
1 | 09/22-10/20 | 1. update some new user stories 2. The algorithm part effectively completed the first two problems, and there have some implement 3. Initial User interface have been designed 4. test case have been designed | N/A | N/A | 1. Complete the design of the backend algorithm,, and implementation 2. Design a complete UI and database, and connect with API | NA | NA | NA | NA | NA | 270.5 | 195.5 | 75 | NA | NA | NA | NA | NA | NA | NA | 1. # of files 2. # of classes 3. # of method 4. # of commit 5. LOC (Length of code) 6.# of person hours used 7. # of user stories completed 8. Time that the program runs
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Shawn
Dawei
Siming
Lijian
Haiyang
Alex

## Shawn Hu
Your Lead Roles: Team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 9 | 7 | 2 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 2 | 0.5 | 1.Bulid initial plan of project 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. | 1. finish Algorithm in 2 weeks, be able to create simple words like hello world project next week 2. Send task assignments to all members again | 0 - continue to learn JavaScript 1 - continue to define requirements 2 - finish Algorithm design | 15
2 | 09/15-09/21 | 15.5 | 12.5 | 3 | 0 - frontend skill learning 1 - Organize tables and plan different schedules 2 - reading literatures and design project algorithm 5 - Make the final decision of each role and assign task. 7 - make ppt for Iteration0 presetation | 3 | 1 | 6 |  |  | 0.5 |  | 2 | 1.Bulid initial Algorithm and make the Flowchart of Algorithm 2. Submit Iteration 0 on git 3. Participate in Iteration 0 presentation 4. Organize meeting documents and set next meeting zoom room 5. Make the final decision of each leader role 6. Make the Group logo | 1.Due to the late selection of the project topic, the algorithm and framework have been designed, but we still need consider about algorithm detail 2. reassign the leader role for team work | 1. finish Algorithm in 1 weeks, be able to create simple words like hello world project next week 2. Send task assignments to all members again | 0 - continue to learn JavaScript 1 - continue to finsih algorithm design 2 - implement a basic hello world on framework | 20
3 | 09/22-09/28 | 9 | 6 | 3 | 0 - learning python 1 - Organize tables and plan different schedules 2 - reading literatures and design project algorithm 5 - communication with teamate to update the project process | 1 | 1 | 2 |  |  | 2 |  |  | 1.Bulid initial Algorithm with first score fomular 2. Organize meeting documents and set next meeting zoom room 3. Make the final decision of each leader role since we have a new teamate | 1. Reassign the leader role for team work and assign the clearly task 2. The progress of the algorithm is very slow, and the activity time of team members is not fixed, so the efficiency is not high | 1. Send task assignments to all members again since we have a new teamate 2. Rearrange the group's activity time and make it mandatory for everyone to show up and encourage active participation | 0 - continue to learn Python Django 1 - continue to finsish algorithm design 2 - implement first formular of score calculate | 15
4 | 09/29-10/05 | 7.5 | 4.5 | 3 | 0 - learning Python 2- design algorithm 4 - manually test the formular 5 - communication with teamate | 1 |  | 1 |  | 0.5 | 2 |  |  | 1.Figure out the representation of the second formular 2.Work out reasonable assignment of team members 3.Communicate project progress with team members | 1.The complexity of the algorithm needs to be reconsidered 2.The developed framework and design need more group discussion | 1.See More Grouping Algorithms to consider the effectiveness of currently used algorithms 2.Improve the effectiveness of the meeting | 0 - continue to learn Python Django 1 - Research the appropriate algorithm for multiple choice and write the formula suitable for our project 2- Start thinking about the project front and back end deployment | 15
5 | 10/06-10/12 | 13.5 | 10.5 | 3 | 0 - learning python Django 1 - thinking about User Storie 2 - design algorithm 4 - learning Test 7 - After listen to team members' progress report and summarize the project progress | 1 | 0.5 | 4 |  | 1 |  |  | 4 | 1.The preliminary algorithm design is completed 2.The front-end template is settled | 1.Implement existing algorithms that have been designed 2.Supervise the group members to complete their respective tasks | 1.Data formats and storage patterns require serious thought 2.The breakdown of tasks needs to be explored | 0 - continue to learn python Django 1 - prepare for iteration 1 2- implement some code source | 20
6 | 10/13-10/19 | 20 | 12 | 8 | 0 - learning python Django 2 - design algorithem 5 - prepare meeting plan 7 - Organize itaeration 1 materials and review the feasibility of each section | 1 |  | 3 |  | 2 |  |  | 6 | 1.The second algorithm is designed and the feasibility of the formula is tested effectively 2.The algorithm report is organized, covering the expression of multiple choice and the derivation process 3.Compiled the itaeration 1 report and submitted 4.Summarized the results reported by team members and updated the development progress | 1.The layout of the whole project, whether it's testing or UI, need consider 2.Need to plan the design of the database and interface | 1.See more UI Design, and survey Design. Find out more about the QA testing section 2.Learn the Django framework and use the code to get what you want | 0-continue learning python Django 1- Complete the whole design of Score cacluate algorithm, write out the formula of the remaining two parts, and test 2-Review ui design and formulate UI specifications 3-Define an algorithm for swapping crew and verify feasibility | 15

## Siming Qian
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07 - 09/14 | 8.5 | 6.5 | 2 | 0 - pick up java front end 1 - define basic level requirements, 5 - set up meeting time, role distribution 6 - set up git 7 - research similar products, prepare presentation | 3 | 0.5 | 0 | 0 | 0 | 2 | 0 | 1 | 1. setting up git 2. role distribution | 1. having trouble find free time in common 2. late start on proj topic | 1. finsih the algorithm | 1. algorithm | 6.5
2 | 09/15 - 09/21 | 8 | 6 | 2 | 0 - java front end learning 1 - get yuting's request from dawei 5 - role distribution again due to a memeber left 7 - reading paper related to algorithm | 3 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 2 | 1. find the algorithm 2. presentation | 1. surprise from the pop due 2. finding the algorithm | 1. finish the algorithm | 1. algorithm 2. java front end | 6
3 | 09/22 - 09/29 | 7.5 | 5.5 | 2 | 0 - python 1 - given that 2 - diagram design 5 - diagram design | 2 | 0.5 | 1 | 0 | 0 | 2 | 0 | 0 | 1. draw the diagram 2. given that 3. touching python | 1. touching python | 1. learning python | 1. learning python 2. algorithm | 7.5
4 | 09/30 - 10/06 | 8 | 6 | 2 | 0 - python 1 - new requirements 2 - fix diagram 5 - diagram, new requirements 7 - algoritm | 1 | 0.5 | 0.5 | 0 | 0 | 2 | 0 | 2 | 1. fix diagram on new requirement 2. touching python 3. algorithm | 1. touching python 2. finding algorithm | 1. learning python 2. finish the algorithm | 1. coding python 2. algorithm | 8
5 | 10/07 - 10/14 | 10 | 7 | 3 | 0 - python, git hub 2 - fix diagram 3 - coding 5 - coding and requriements 7 - algorithm | 0.5 | 0 | 0.5 | 2 | 0 | 2 | 0 | 2 | 1. fix diagram 2. coding 3. algorithm | 1. coding 2. fiding algorithm | 1. coding python 2. finished the algorithm | 1. coding python 2. algorithm | 10

## Dawei Yin
Your Lead Roles: Design & Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 10 | 8 | 2 | 0 - pick up java and its frameworks 1 - define high level requirements, 5 - make project plan 6 - set up git 7 - research similar algorithms | 3 | 1 |  | 0 | 0 | 1 | 2 | 1 | 1.Bulid initial plan of project 2. Set up git, commit a test message on git | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. | 1. finish Algorithm in 2 weeks, be able to create simple words like hello world project next week 2. Send task assignments to all members again | 0 - continue to design algorithm for the project 1 - continue to define requirements 3 - implement a basic hello world on framework | 10
2 | 09/15-09/21 | 16.5 | 13.5 | 3 | 0 - read the research papers 1 - analysis the requirement for the iGroup project 2 - try to come up a valid algorithm for this project 5 - commute with professor and document the requirements 6 - set up java development environment | 3 | 2 | 4 | 0 | 0 | 1.5 | 1 | 2 | 1. gather the info for the project requirements from the instructor 2. set up development environment 3. keep working on the algorithm | 1. it might take more time on designing valid algorithm than we expected for this project | 1. set a deadline on designing the algorithm, if we cannot make it, we might consider to change our project proposal. | 1. come up a valid algorithm 2. design the architecture for the implementation of this algorithm | 15
3 | 09/22-09/29 | 12 | 9 | 3 | 0 - continue read the resarch paper and search related feature 2 - design the class structure 5 - discuss the structure with teammates | 3 | 0 | 6 | 0 | 0 | 3 | 0 | 0 | 1. design the UML class diagram for the allocation system and survey system. 2. Clear the teammates' confusion toward my class design | 1. The multiple choice objective score function in the paper is not fullfilled the instructor's requirement. 2. Change language from Java to python, which may lead to some extra learning curve for this project. | 1. Need to modify the origin objective function for calculating multiple choice question 2. Learn python asap | 1. Find a solution to calculate the multiple choices score for each team 2. Implement the objetive score function for calculating the single choice 3. Keep researching | 15
4 | 09/30- 10/07 | 20 | 19 | 1 | 0 - look into the new paper: single choice question 2 - design all survey system class for this project 3 - implement the survey class and single choice objective score function in python 4 - write a sample for illustrating how the class work 5 - updated my progress to the team | 5 | 0 | 5 | 8 | 1 | 1 | 0 | 0 | 1. Implemented the ability to calculate the single choice objetive score function for a team 2. Built multiple classes for building survey and allocation 3. Write a sample scripts to illustrate how the classes work | 1. Need to define the survey input data format from student | 1. JSON format response from student | 1. Modify and Implement the objective score function of multiple choice question 2. design the algorithm to swap the team members 3. | 20
5 | 10/08 - 10/18 | 23 | 15 | 8 | 0 - looked into the new paper: multiple choice question 2 - designed the allocation system 3 - implemented the multiple choice objective score function in python 5 - continued working on writing scripts to illustarte how the class work, also work with Shawn together to modify the multiple choice objective score function to take the preference into consideration. | 5 | 0 | 2 | 8 | 0 | 8 | 0 | 0 | 1. Implemented the ability to calculate the multiple choice objetive score function for a team 2. Graphed the Allocation system classs diagram 3. Designed and modified the origin multiple choice score objective function for a team | 1. Need to come up with a solution to take the self-defined weight from student into consideration | 1. Remove the feature for adding the self-define weight for multiple choices | 1. Add the swaping funcionality 2. Draft tests to test our algorithm | 20
6 | 10/19 - |  |  |  | 0 - keep learning the algorithm 2 - design the instance class and swap pesudocode 3 - implement swap 5 - show teams how the swap work

## Alex Wang
Your Lead Roles: Security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07 - 09/14 | 8.5 | 6.5 | 2 | 0 - pick up java front end 1 - define basic level requirements, 5 - set up meeting time, role distribution 6 - set up git 7 - research similar products, prepare presentation | 3 | 0.5 | 0 | 0 | 0 | 2 | 0 | 1 | 1. setting up git 2. role distribution | 1. having trouble find free time in common 2. late start on proj topic | 1. finsih the algorithm | 1. algorithm | 6.5
2 | 09/15 - 09/21 | 8 | 6 | 2 | 0 - java front end learning 1 - get yuting's request from dawei 5 - role distribution again due to a memeber left 7 - reading paper related to algorithm | 3 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 2 | 1. find the algorithm 2. presentation | 1. surprise from the pop due 2. finding the algorithm | 1. finish the algorithm | 1. algorithm 2. java front end | 6
3 | 09/22 - 09/29 | 7.5 | 5.5 | 2 | 0 - python 1 - given that 2 - diagram design 5 - diagram design | 2 | 0.5 | 1 | 0 | 0 | 2 | 0 | 0 | 1. draw the diagram 2. given that 3. touching python | 1. touching python | 1. learning python | 1. learning python 2. algorithm | 7.5
4 | 09/30 - 10/06 | 8 | 6 | 2 | 0 - python 1 - new requirements 2 - fix diagram 5 - diagram, new requirements 7 - algoritm | 1 | 0.5 | 0.5 | 0 | 0 | 2 | 0 | 2 | 1. fix diagram on new requirement 2. touching python 3. algorithm | 1. touching python 2. finding algorithm | 1. learning python 2. finish the algorithm | 1. coding python 2. algorithm | 8
5 | 10/07 - 10/14 | 10 | 7 | 3 | 0 - python, git hub 2 - fix diagram 3 - coding 5 - coding and requriements 7 - algorithm | 0.5 | 0 | 0.5 | 2 | 0 | 2 | 0 | 2 | 1. fix diagram 2. coding 3. algorithm | 1. coding 2. fiding algorithm | 1. coding python 2. finished the algorithm | 1. coding python 2. algorithm | 10
6 | 10/14 - 10/19 | 8 | 6 | 2 | 0 - python, git hub 2 - fix diagram 3 - Django 5 - coding and requriements

## Lijian Yao
Your Lead Roles: Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 7 | 5 | 2 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 |  |  |  |  | 0.5 | 1 | 0.5 | 1.Set up git 2.Set up a team 3.communication plan 4.Meet teammates | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. | 1.Finishing up Algorithm within few week | 1. Learning 2. Finishing SPP doc 3.Prepare for Presentation | 7
2 | 09/14-09/21 | 7 | 5 | 2 | 0 - read several tutorials, choose the best tool to use for our team 5 - make project plan, received all the task assigned by team leader 6 - set up git, finishing up the SPPP doc 7 - Prepare presentation | 3 |  |  |  |  | 0.5 | 1 | 0.5 | 1.Finished SPPP doc 2.Prepare for presentation 3.Finishing up Algorithm | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. 3.We lost a Teammate so we had to fill in his role | 1.Finishing up Algorithm within few week | 1. Learning 2.Framework 3.Algorithm more TBD by next meeting | 7
3 | 09/22-09/29 | 7 | 5 | 2 | 0-learn algorithm part assigned by team leader 5-make sure everyone is doing their job so no duplicate work 6-learn how to use Pivotal Tracker 7-prepared for Lab2 | 3 |  |  |  |  | 0.5 | 1 | 0.5 | 1.Finished SPPP doc 2.Help Setting up Pivotal Tracker for every group members. 3.Finishing up Algorithm | 1.Almost everyone in our team only familar with backend so I am now the one who responsible for the UI. 2.Communiaction is getting better. | 1.Learning all the required things | 1.Learning 2.UI 3.communicating | 10
4 | 09/30- 10/07 | 12 | 10 | 2 | 0-learn how to create UI & HTML & paper 5-communicate with teammates for what UI page do we need 7-quiz | 8 |  |  |  |  | 1 |  | 1 | 1.Get UI pages design mindset sorted out 2.get all the learning done(UI) 3.Ask leader for things to do 4.Finished quiz | 1.Learning UI design and everything is new for me but I am kind of enjoying it | 1.Get the UI pages done 2.learning | 1.Learning 2.design UI pages 3.communicating | 14
5 | 10/08 - 10/14 | 20 | 18 | 2 | 0-learn how to create UI & HTML 2-design the UI pages 5 - asked group memeber what function they want in the UI pages and get the UI preview set up 7-perpared for presentation | 7 |  | 8 |  |  | 0.5 | 1 | 1.5 | 1.Get some UI page done 2.prepared for presentation 3.ready to submit iteration1 | 1.Spend too much time to make things perfect. | 1.Get more UI pages done 2.learning | 1.Learning 2.link up some UI pages 3.communicating | 15
6 | 10/14 - | 20 | 18 | 2 | 0-learn how to create UI & HTML 2-design more UI pages 5 - asked group memeber what function they want in the UI pages and get the UI preview set up 7-review class material | 7 |  | 8 |  |  | 0.5 | 1 | 1.5 | 1.Get more UI page done 2.more learning 3.ready to submit iteration1 |  | 1.Get more UI pages done 2.learning | 1.Learning 2.link up some UI pages 3.communicating | 15

## Haiyang Wang
Your Lead Roles: QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 8 | 6 | 2 | 0 - learn git, github, github desktop, 1 - define high level requirements, 5 - make project plan, send reminders to team members, 6 - set up git, 7 - research similar products, prepare presentation. | 3 | 1 | null | null | null | 0.5 | 1 | 0.5 | 1.Bulid initial plan of project 2. Set up git, commit a test message on git 3. Participate in Iteration 0 | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet, 2. communication is not clear. Task assignments is not clear. | 1. Communicate with teammates, frame design decided, 2. Task assignments successfully finished | 1. Reading References, 2. Finish Algorithum design | 6 - 12
2 | 09/15-09/21 | 10 | 7 | 3 | 0 - learn basic contents of testing, 1 - analysis the requirement for the iGroup project, 2 - reading literatures and design project algorithm, 5 - Make the final decision of each role together. 7- Finish sessions in SPPP, SPPP_RiskManagement | 3 | 1 | 3 | null | null | 0.5 | null | 2.5 | 1. Finish QA session in SPPP, finish testing and integration sessions in SPPP_RiskManagement, 2. Participate in Iteration 0 presentation | 1. Due to the late selection of the project topic, although the algorithm and framework have been designed, we still need consider about algorithm detail 2. leader role for team work is not clear | 1. finish Algorithm in 1 weeks, 2. Get the role, tasks finished | 1. Reading References, 2. Finish Algorithum design 3. Learn more about testing | 9 - 15
3 | 09/22-09/28 | 9 | 7 | 2 | 0 - learn algorithm, learn tests 5 - Coworking 6 - learn Pivotal Tracker 7- preparing Lab2 | 4 | null | null | null | null | 2 | 1 | 2 | 1. Modify SPPP 2. Setting Pivital Trakcer 3. Start to think about the basic of tests | 1. New on Pivotal Tracker | 1. Start learning it | 1. Reading 2. Learning tests concepts 3. lab 2 | 9 - 15
4 | 09/29- 10/05 | 10 | 8 | 2 | 0 - learn tests on python 1 - designing model of tests 5 - co working 7 - lab2 | 6 | 2 | null | null | null | 2 | null | null | 1. Design the frame of tests 2. Write some user story | 1. My user storirs have mistakes | 1. Modify the stories, problem solved | 1. Reading 2. Learning tests concepts 3. design model | 9 - 15
5 | 10/06 - 10/12 | 12 | 8 | 4 | 0 - learn tests on python 1 - designing model of tests 5 - talk about what should we do in the future 6 - set up git enviroment | 4 | 2 | null | null | null | 4 | 2 | null | 1. thinking about what should we test 2. Design test model | 1. Not all algorithms are finished, only start writing about obout other tests | 1. Waiting for complete | 1. Reading 2. Learning tests on python 3. Writing some test | 9 - 15
6 | 10/13 - 10/20 | 12 | 8 | 4 | 0 - learn tests on python 4 - write some tests about init 5 - talk about metrix and futurn tests 7 - modify SPPP | 2 | null | null | null | 4 | 4 | null | 2 | 1. Write some tests 2. Modify SPPP | 1. Not all algorithms are finished, only start writing about obout other tests | 1. Waiting for complete, write some tests first | 1. Reading 2. Continue to learn tests on python 3. Writing more test | 9 - 15