## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | length of code
0 | 09/07- 09/21 | 1. Roles assigned 2. Setup github 3. Finalized project idea 4. Determing the devalopment tool which we will use 5. Bulid Initial Algorithm plan 6. Make the Logo of our project | N/A | N/A | In progress | NA | NA | NA | NA | NA | 104 | 74 | 30 | NA | NA | NA | NA | NA | NA | NA | NA
1 | 09/22-10/20 | 1. update some new user stories 2. The algorithm part effectively completed the first two problems, and there have some implement 3. Initial User interface have been designed 4. test case have been designed | Lots of teammate don't have Django experience | task discelear | 1. Complete the design of the backend algorithm,, and implementation 2. Design a complete UI and database, and connect with API | NA | 2 | 2 | 0 | 2 | 270.5 | 195.5 | 75 | 55.5 | 6 | 29 | 43 | 7 | 57 | 73 | 478
2 | 10/21-11/11 | 1. Finished some features ( login, logout, connect Django with Algorithm, create instance,delete instance, create survey, create question, create options, create student answer and submit, save the date into Django database,etc..) | 1. front-end UI design could not be use recently. 2.Some function need test code 3.The development progress is too slow, the team members have different technical abilities | 1.Communication patterns need to be recalibrated and more effective teamwork required | 1.Implemente all the features we designed before iteration 3 2. Debug for our algorithm. 3. Fixing the existing bug 4. Implemente whole system test | 5 | 8 | 4 | 0 | 4 | 336 | 278 | 58 | 64.5 | 2 | 36.5 | 64 | 29 | 47 | 35 | 5341
3 | 11/12-12/10 | Finished All application‘s features which are included 1.User Login and Logout 2.Implement Algorithm into Application by Django 3.Import survey data csv and student answer data features 4.Survey Create and Edit 5.Lock Survey Link 6.Student Answer Submission Link 7.Team Assign Results 8. Results History | 1. UI Design not perfect match 2. Apps haven't been tested with a lot of data yet 3. Teamates have different abilities and one member has done a lot | The group's meeting time doesn't match for everybody | Iteration 3 is the final Iteration | 12 | 0 | 12 | 8 | 4 | 314.5 | 271 | 43.5 | 67 | 15 | 38 | 88.5 | 39.5 | 66 | 56 | 12140

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Shawn | 1, Overvie, Related Work, Management Plan, Reference 2, Update and Revise all Iterations | Add fews User Stories | 1, Introduction 2, Business Logic and/or Key Algorithms 3, References 4, Update and Revise all Iterations |  | All Iterations Prepare PPT Presentation | fews refactor code review | fews Unitest of source_code |  | 1, Organize Meetings and Make meeting minutes 2, Summrize all progress reports from team members 3, Assign task for each role
Dawei | Code review |  | 1. Database design 2. System architecture | 1. All testing regards to the Django implementaion | All Iteration: Design and implmentation iteration 3: Demo | Django framework codes(Account, Survey, iGroup) (models,views, forms, utils, algorithm services, and some templates) & algorithm codes | In Django: iGroup: view tests, url tests Account: view test, url tests, form tests Survey: view test, url tests |  | Making tutorial vidoes
Siming | Proposed High level Requirements | Management
Lijian | Configuration Management Plan |  | All UI-Documents |  | iteration 0 & final presentation | Connection between front end & back |  |  | Most of the meeting
Haiyang | QA part |  |  | 1. Part of Testing Summary 2. Part of Manual Testing Report Including: test_questions (app) test_surveys (app) test_answers (app) test_answer_sheets (app) test_single_choice_score (app) test_multiple_choice_answer (app) test_teams (app) test_weight (whole source code file / web not include) test_mixed_questions_weight (whole source code file / web not include) test_for_effects_of _more_choices (whole source code file / web not include) test_for_effects_of _more_questions (whole source code file / web not include) test_for_effects_of _num_of_teams (whole source code file / web not include) | qa part of presentation 1 | some refactory of the source code | test_questions (app) test_surveys (app) test_answers (app) test_answer_sheets (app) test_single_choice_score (app) test_multiple_choice_answer (app) test_teams (app) test_weight (whole source code file / web not include) test_mixed_questions_weight (whole source code file / web not include) test_for_effects_of _more_choices (whole source code file / web not include) test_for_effects_of _more_questions (whole source code file / web not include) test_for_effects_of _num_of_teams (whole source code file / web not include) |  | Attend to meeting as much as possible unless there is special condition
Ruotong | Security Requirement change password | Some User stories | Database Desigin / Design Pattern MVC /Security Design / test model |  | database design Architecture subsystem in Iteration2 MVC | model of group | security test in SDD | database/ model in Django | except for the earlest two meeting because of adding course in week3, all

## Shawn Hu
Your Lead Roles: Team leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 9 | 7 | 2 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 2 | 0.5 | 1.Bulid initial plan of project 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. | 1. finish Algorithm in 2 weeks, be able to create simple words like hello world project next week 2. Send task assignments to all members again | 0 - continue to learn JavaScript 1 - continue to define requirements 2 - finish Algorithm design | 15
2 | 09/15-09/21 | 15.5 | 12.5 | 3 | 0 - frontend skill learning 1 - Organize tables and plan different schedules 2 - reading literatures and design project algorithm 5 - Make the final decision of each role and assign task. 7 - make ppt for Iteration0 presetation | 3 | 1 | 6 |  |  | 0.5 |  | 2 | 1.Bulid initial Algorithm and make the Flowchart of Algorithm 2. Submit Iteration 0 on git 3. Participate in Iteration 0 presentation 4. Organize meeting documents and set next meeting zoom room 5. Make the final decision of each leader role 6. Make the Group logo | 1.Due to the late selection of the project topic, the algorithm and framework have been designed, but we still need consider about algorithm detail 2. reassign the leader role for team work | 1. finish Algorithm in 1 weeks, be able to create simple words like hello world project next week 2. Send task assignments to all members again | 0 - continue to learn JavaScript 1 - continue to finsih algorithm design 2 - implement a basic hello world on framework | 20
3 | 09/22-09/28 | 9 | 6 | 3 | 0 - learning python 1 - Organize tables and plan different schedules 2 - reading literatures and design project algorithm 5 - communication with teamate to update the project process | 1 | 1 | 2 |  |  | 2 |  |  | 1.Bulid initial Algorithm with first score fomular 2. Organize meeting documents and set next meeting zoom room 3. Make the final decision of each leader role since we have a new teamate | 1. Reassign the leader role for team work and assign the clearly task 2. The progress of the algorithm is very slow, and the activity time of team members is not fixed, so the efficiency is not high | 1. Send task assignments to all members again since we have a new teamate 2. Rearrange the group's activity time and make it mandatory for everyone to show up and encourage active participation | 0 - continue to learn Python Django 1 - continue to finsish algorithm design 2 - implement first formular of score calculate | 15
4 | 09/29-10/05 | 7.5 | 4.5 | 3 | 0 - learning Python 2- design algorithm 4 - manually test the formular 5 - communication with teamate | 1 |  | 1 |  | 0.5 | 2 |  |  | 1.Figure out the representation of the second formular 2.Work out reasonable assignment of team members 3.Communicate project progress with team members | 1.The complexity of the algorithm needs to be reconsidered 2.The developed framework and design need more group discussion | 1.See More Grouping Algorithms to consider the effectiveness of currently used algorithms 2.Improve the effectiveness of the meeting | 0 - continue to learn Python Django 1 - Research the appropriate algorithm for multiple choice and write the formula suitable for our project 2- Start thinking about the project front and back end deployment | 15
5 | 10/06-10/12 | 13.5 | 10.5 | 3 | 0 - learning python Django 1 - thinking about User Storie 2 - design algorithm 4 - learning Test 7 - After listen to team members' progress report and summarize the project progress | 1 | 0.5 | 4 |  | 1 |  |  | 4 | 1.The preliminary algorithm design is completed 2.The front-end template is settled | 1.Implement existing algorithms that have been designed 2.Supervise the group members to complete their respective tasks | 1.Data formats and storage patterns require serious thought 2.The breakdown of tasks needs to be explored | 0 - continue to learn python Django 1 - prepare for iteration 1 2- implement some code source | 20
6 | 10/13-10/19 | 20 | 12 | 8 | 0 - learning python Django 2 - design algorithem 5 - prepare meeting plan 7 - Organize itaeration 1 materials and review the feasibility of each section | 1 |  | 3 |  | 2 |  |  | 6 | 1.The second algorithm is designed and the feasibility of the formula is tested effectively 2.The algorithm report is organized, covering the expression of multiple choice and the derivation process 3.Compiled the itaeration 1 report and submitted 4.Summarized the results reported by team members and updated the development progress | 1.The layout of the whole project, whether it's testing or UI, need consider 2.Need to plan the design of the database and interface | 1.See more UI Design, and survey Design. Find out more about the QA testing section 2.Learn the Django framework and use the code to get what you want | 0-continue learning python Django 1- Complete the whole design of Score cacluate algorithm, write out the formula of the remaining two parts, and test 2-Review ui design and formulate UI specifications 3-Define an algorithm for swapping crew and verify feasibility | 15
7 | 10/20 - 10/26 | 10 | 6 | 4 | 0 - learning Python& Djiango 2 - design url discussion 5 - communication/management | 2 |  | 2 |  |  | 2 |  |  | 1, discuss about url design 2. Summarized the results reported by team members and updated the development progress | 1.The progress in the group was slow and the members did not know their tasks 2. The project structure is not clear | 1,Increase the frequency of checking in with group members, and make notes so people can watch the replay 2, Re-make he design of the project progress | 0-Continue learning python Django 1-implement some function feature by code | 10
8 | 10/27 - 11/02 | 16 | 11 | 5 | Individual Task Breakdown 0 - learning Python& Djiango 1 - requirement analysis 3 - make implementation 4 - try to write unit test code 5 - communication/management | 2 | 1 |  | 2 | 2 | 4 |  |  | 1. comfirm the user story of whole project 2. learn the test code format 3. Summarized the results reported by team members and updated the development progress | 1. Hard to catch up the progress of project | 1, focus on learning django, not group connection | 0-Continue learning python Django 1-implement some function feature by code | 10
9 | 11/03 - 11/09 | 20 | 16 | 5 | Individual Task Breakdown 0 - learning Python& Djiango 3 - implementation 5 - communication/management 6 - make sure the whole group have same environment | 6 |  |  | 3 |  | 5 | 1 |  | 1,Compiled the itaeration 2 report and submitted 2,catch up the development and try the 'delete button' and still working on 3, organize some group stuff | 1.The development of the project is too slow, personnel and technology are not equal. | 1. Adopt alternate plans for the development of the project, focusing on some team members | 0-Continue learning python Django 1-implement delete and lock feature 2-debug the algorithm code 3- re-summary the algorithm swap method | 20
10 | 11/10 - 11/16 | 8.5 | 5.5 | 3 | 0 - learning Django 3 - Algorithm Debug 4 - test source_code 5 - communication/management | 1 |  |  | 0.5 | 1 | 3 |  |  | 1, Refactor code (algorithm part) 2, Re-summary the algorithm swap method | 1.The development of the project is too slow, personnel and technology are not equal. | 1. Adopt alternate plans for the development of the project, focusing on some team members | 0-Continue learning python Django 1-implement delete and lock feature 2- start code review | 20
11 | 11/17 - 11/23 | 9 | 7 | 2 | 0 - learning Django 2- make the Analong Data 5 - communication/management 7 - Organize Meeting minutes | 2 |  | 2.5 |  |  | 2 |  | 0.5 | 1, Organize the Meeting Minutes 2, fews Unittest code of source_code 3.Made student answer and survey data | 1.The development of the project is too slow, personnel and technology are not equal. | 1. Adopt alternate plans for the development of the project, focusing on some team members | 0-Continue learning python Django 1-implement back feature 2- Try to make UI connect | 10
12 | 11/24 -11/30 | 8 | 6 | 2 | 0 - learning Django 2 - Debug of Algorithem 5 - communication/management | 3 |  | 2 |  |  | 1 |  |  | 1, Summarized the results reported by team members and updated the development progress | Due to the thanksgiving, hard to organize teamates at same time | Make warmming to group member and update the meeting records | 0-Continue learning python Django 1- Try to make UI connect 2 - Prepare for Iteration3 | 20
13 | 12/01 - 12/10 | 10 | 9 | 2 | 0 - Leaning Django 3 - Revise and comfirm all the documents 5 - communication/management 7 - Prepare Iteration 3 | 3 |  |  | 2 |  | 2 |  | 2 | 1,Compiled the itaeration 3 report and submitted 2, Final Presentation 3, Manage the source of GItHub and write the README | we are implememnt some basic features, but not fancy | NA | NA

## Dawei Yin
Your Lead Roles: Design & Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 10 | 8 | 2 | 0 - pick up java and its frameworks 1 - define high level requirements, 5 - make project plan 6 - set up git 7 - research similar algorithms | 3 | 1 |  | 0 | 0 | 1 | 2 | 1 | 1.Bulid initial plan of project 2. Set up git, commit a test message on git | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. | 1. finish Algorithm in 2 weeks, be able to create simple words like hello world project next week 2. Send task assignments to all members again | 0 - continue to design algorithm for the project 1 - continue to define requirements 3 - implement a basic hello world on framework | 10
2 | 09/15-09/21 | 16.5 | 13.5 | 3 | 0 - read the research papers 1 - analysis the requirement for the iGroup project 2 - try to come up a valid algorithm for this project 5 - commute with professor and document the requirements 6 - set up java development environment | 3 | 2 | 4 | 0 | 0 | 1.5 | 1 | 2 | 1. gather the info for the project requirements from the instructor 2. set up development environment 3. keep working on the algorithm | 1. it might take more time on designing valid algorithm than we expected for this project | 1. set a deadline on designing the algorithm, if we cannot make it, we might consider to change our project proposal. | 1. come up a valid algorithm 2. design the architecture for the implementation of this algorithm | 15
3 | 09/22-09/28 | 12 | 9 | 3 | 0 - continue read the resarch paper and search related feature 2 - design the class structure 5 - discuss the structure with teammates | 3 | 0 | 6 | 0 | 0 | 3 | 0 | 0 | 1. design the UML class diagram for the allocation system and survey system. 2. Clear the teammates' confusion toward my class design | 1. The multiple choice objective score function in the paper is not fullfilled the instructor's requirement. 2. Change language from Java to python, which may lead to some extra learning curve for this project. | 1. Need to modify the origin objective function for calculating multiple choice question 2. Learn python asap | 1. Find a solution to calculate the multiple choices score for each team 2. Implement the objetive score function for calculating the single choice 3. Keep researching | 15
4 | 09/29- 10/05 | 20 | 19 | 1 | 0 - look into the new paper: single choice question 2 - design all survey system class for this project 3 - implement the survey class and single choice objective score function in python 4 - write a sample for illustrating how the class work 5 - updated my progress to the team | 5 | 0 | 5 | 8 | 1 | 1 | 0 | 0 | 1. Implemented the ability to calculate the single choice objetive score function for a team 2. Built multiple classes for building survey and allocation 3. Write a sample scripts to illustrate how the classes work | 1. Need to define the survey input data format from student | 1. JSON format response from student | 1. Modify and Implement the objective score function of multiple choice question 2. design the algorithm to swap the team members 3. | 20
5 | 10/06 - 10/12 | 23 | 15 | 8 | 0 - looked into the new paper: multiple choice question 2 - designed the allocation system 3 - implemented the multiple choice objective score function in python 5 - continued working on writing scripts to illustarte how the class work, also work with Shawn together to modify the multiple choice objective score function to take the preference into consideration. | 5 | 0 | 2 | 8 | 0 | 8 | 0 | 0 | 1. Implemented the ability to calculate the multiple choice objetive score function for a team 2. Graphed the Allocation system classs diagram 3. Designed and modified the origin multiple choice score objective function for a team | 1. Need to come up with a solution to take the self-defined weight from student into consideration | 1. Remove the feature for adding the self-define weight for multiple choices | 1. Add the swaping funcionality 2. Draft tests to test our algorithm | 20
6 | 10/13 - 10/19 | 12 | 9 | 3 | 0 - keep learning the algorithm 2 - design the instance class and swap pesudocode 3 - implement swap 5 - show teams how the swap work | 1 | 0 | 6 | 3 | 0 | 2 | 0 | 0 | 1. Pesudocode for climbing hill algorithm 2. Created and modified the class correspondingly | 1. inconsistancy comprehension of the climbing hill algorithm among the team members | 1. Devote more time to help the team understand | 1. Implemented the pesudocode 2. Create tests to tests the functionality | 15
7 | 10/20 - 10/26 | 12 | 10 | 2 | 0 - learning bascis of Django 2 - design URL and django app schema 3 - Implment data base model 5 - assign tasks for team members | 4 | 0 | 3 | 3 | 0 | 2 | 0 | 0 | 1. Create skeleton of Django 2. Config models for different apps | 1. security concerns about user authentication | 1. Inherit django auth user to avoid complicated user authentication process | 1. Implement user, survey, and instance controller | 20
8 | 10/27 - 11/3 | 28 | 24 | 3 | 0 - learn how to use js and django advance view technics 2 - design the view functions for iGroup/Survey 3 - implment all the views function in iGroup and Survey sub app 4 - design and write test cases for instance validation 5 - teach all group members how our project work | 5 | 0 | 3 | 10 | 6 | 4 | 0 | 0 | 1. implement basic view functions for instance creation, survey creaction 2. implment the JS script for dynamic adding survey question | 1. require a large amount of learning time | 1. spend more time to learn | 1. Implement and integrate iGroup app to our main web application | 20
9 | 11/3 - 11/9 | 22 | 17 | 5 | 0 - learning how django 2 - design part of the database to record student answer to a survey 3 - Implement the functionality for student to answer the survey and run the algorithm base on the survey 4 - write test cases for the survey 5 - record django coding tutorial for our group, and meeting | 3 | 0 | 3 | 9 | 2 | 5 | 0 | 0 | 1. Now student can answer the survey 2. Instructor can run algorithm base on the response of the student | 1. test coverage is low | 1. build more tests cases | 1. build more tests 2. Fix known bugs 3. Integrate back end with front end 4. Implement import csv features | 30
10 | 11/9 - 11/16 | 22 | 20 | 2 | 0 - learning Django test framework 2 - design the middleware to provide the services for student survey and iGroup algorithm 3 - Implement the services 5 - group meeting & communication | 2 | 0 | 8 | 10 | 0 | 2 | 0 | 0 | 1. The django views can use the service provided by the middleware to run algorithm 2. Some survey test cases | 1. front end is not looking good | 1. James can improve the front end | 1. build the functionality to let instructor to upload the survey from csv file. | 20
11 | 11/17 - 11/23 | 19 | 18 | 1 | 0 - learning Django form manipulation 2 - design functionality to let instructor to build survey by uploading survey csv file 3 - Implement the uploading survey utility 4 - keep writing test cases for the survey 5 - group meeting & communication | 2 | 0 | 5 | 10 | 1 | 1 | 0 | 0 | 1. Now instructor can upload the survey from csv file | 1. need some test cases for testing the uploading survey functionality | 1. write some test cases in next week | 1. build the functionality to let instructor to upload the student response from csv file. 2. provide the functionality to let instructor to learn the progress of student who answer the survey | 30
12 | 11/24 -11/30 | 29 | 28 | 1 | 0 - learning Django form manipulation 2 - design functionality to let instructor to upload student answers, and design the controller that allow instructor to see all the student who response to the survey and their reponses 3 - Implement the uploading student response from csv utility, and checking student progress functionalities 4 - keep writing test cases for the survey 5 - group meeting & communication | 2 | 0 | 10 | 15 | 1 | 1 | 0 | 0 | 1. Now instructor can upload the student response from csv file 2. Now instructor can see all the student who answer the survey and their responses | 1. Need some test cases in general 2. Need to improve the front end | 1, Ask other teammate for writing some more test cases 2. Use bootstrap for front end | 1. Implement functionality for instructor to see the result from runing the alogrithm 2. prepare iter 3 | 30
13 | 12/01 - 12/10 | 34 | 29 | 5 | 0 - learning Django front end technics 2 - design the controllor & view for showing grouping result and their specific scores 3 - Implement the beautify front end with James & get the survey response link Implement the functionality for showing the grouping result and their specific scores 4 - keep writing test cases for the survey 5 - group meeting & communication & presentation | 3 | 0 | 10 | 15 | 1 | 5 | 0 | 0 | 1. Now instructor can see all the grouping formation from each result 2. Somewhat improved front end 3. PPT for presentation | 1. Need some test cases in general 2. Need to improve the front end | Nothing

## Siming Qian
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07 - 09/14 | 8.5 | 6.5 | 2 | 0 - pick up java front end 1 - define basic level requirements, 5 - set up meeting time, role distribution 6 - set up git 7 - research similar products, prepare presentation | 3 | 0.5 | 0 | 0 | 0 | 2 | 0 | 1 | 1. setting up git 2. role distribution | 1. having trouble find free time in common 2. late start on proj topic | 1. finsih the algorithm | 1. algorithm | 6.5
2 | 09/15 - 09/21 | 8 | 6 | 2 | 0 - java front end learning 1 - get yuting's request from dawei 5 - role distribution again due to a memeber left 7 - reading paper related to algorithm | 3 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 2 | 1. find the algorithm 2. presentation | 1. surprise from the pop due 2. finding the algorithm | 1. finish the algorithm | 1. algorithm 2. java front end | 6
3 | 09/22 - 09/29 | 7.5 | 5.5 | 2 | 0 - python 1 - given that 2 - diagram design 5 - diagram design | 2 | 0.5 | 1 | 0 | 0 | 2 | 0 | 0 | 1. draw the diagram 2. given that 3. touching python | 1. touching python | 1. learning python | 1. learning python 2. algorithm | 7.5
4 | 09/30 - 10/06 | 8 | 6 | 2 | 0 - python 1 - new requirements 2 - fix diagram 5 - diagram, new requirements 7 - algoritm | 1 | 0.5 | 0.5 | 0 | 0 | 2 | 0 | 2 | 1. fix diagram on new requirement 2. touching python 3. algorithm | 1. touching python 2. finding algorithm | 1. learning python 2. finish the algorithm | 1. coding python 2. algorithm | 8
5 | 10/07 - 10/14 | 10 | 7 | 3 | 0 - python, git hub 2 - fix diagram 3 - coding 5 - coding and requriements 7 - algorithm | 0.5 | 0 | 0.5 | 2 | 0 | 2 | 0 | 2 | 1. fix diagram 2. coding 3. algorithm | 1. coding 2. fiding algorithm | 1. coding python 2. finished the algorithm | 1. coding python 2. algorithm | 10
6 | 10/15 - 10/22 | 8.5 | 5.5 | 3 | 0 - python, github multi devices 1 - adding new requirements 2 - sorting requirements 5 - manage pivoat tracker | 1 | 1 | 1 | 1 | 0 | 1.5 | 0 | 0 | 1. adding requirements 2. sorting requirements 3. manage pivoat tracker 4. implementation | 1. duplicated requirements founded 2. some requirements become uncessary | 1. delete duplicated or unecessary requirements 2. update requirements to fit the design 3. going back to pivoat tracker and manage all requirements | 1. front end, determine pages needed 2. adding funtion and test | 8.5
7 | 10/23 - 10/30 | 9 | 5 | 4 | 0 - python 1 - go through requirements for web page implementation 2 - deteremine web pages needed based on requirements 3 - adding functions in user.py 4 - write tests of added funtion 5 - handle web pages to team leader | 0.5 | 0.5 | 1.5 | 1 | 1 | 0.5 | 0 | 0 | 1. list web pages needed by user story 2. sketch webpages with buttons and its directed pages 3. implement 4. write test | 1. some requirements may not be implemented 2. differ opinions | 1. move those requirements to optional/ desireable category 2. implementation 3. testing | 1. front end of each page 2. picking up on front end pop up window 3. helping around | 9
8 | 10/31 - 11/7 | 4 | 4 | 0 | 0 - brifely picking up front end, reading through existing front end code to learn 3 - write down codes of the front end when learning 6 - members are using different python/pycharm versions | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1. read front end codes 2. adding code of course title implmementation | 1. had a weekend out of town 2. need to catch up | 1. go through meeting record 2. go through updated codes | 1. connect each with its back end 2. implementation 3. tests | 4
9 | 11/8 - 11/15 | 12.5 | 12.5 |  | 0 - learning on django and mvc model 1 - adding new requirement of import student data with cvs file 2 - design the import feature 3 - writting down local code 5 - update pivotal tracker, rebasing pivotal track requirements. 7 - little research on project management | 5 | 0.5 | 0 | 3 | 0 | 3 | 0 | 1 | 1. learning on mvc model to try to implement 2. adding new requirement 3. update pivotal tracker to manage progress | 1. not much coding 2. need to keep track with everyones progress for update 3. need to category requirements | 1. keep cathing on django 2. more communication on everyone's progress 3. more works on pivotal tracker | 1. learning on django 2. tacking on progress 3. check on requirements to category | 12.5
10 | 11/16 - 11/23 | 16.5 | 16.5 |  | 0 - learning on django 1 - category requirements (chore) 2 - discuss about if some fetures are being essential 3 - create own branch, writting down local code 5 - update pivotal tracker, update features based on discuss, category some feature to chore 7 - check on team progress | 5 | 1.5 | 1 | 4 | 0 | 4 | 0 | 1 | 1. learning on dajngo and tryng to implement 2. update requirements 3. update pivotal tracker to manage progress 4. check on team progress | 1. hard to catch the coding progress 2. many requirements turned into optional 3. experiencing communication difficulty (probably becuz its before thx giving) | 1. keep cathing and try to contribute the team some other way 2. more communications 3. keep updating the pivotal tracker | 1. check on progress 2. requirements check up 3. learning django prepare for presentation | 16.5
11 | 11/24 - 12/1 | 3 | 3 |  | 1 - final check up on requriements 5 - update pivotal tracker 7 - prepare for presentation | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 1. update pivotal tracker | 1. having health issues, cant setting on chairs and perform works. | 1. try to recover | 1. prepare for presentation 2. update pivotal tracker | 3
12 | 12/2 - 12/9 | 2 | 2 |  | 5 - check on progress and update pivotal tracker 7 - prepare for presentation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1. update pivotal tracker 2. prepare for presentation | 1 not fully recovered from health issue | 1. revocer | 1. final | 2

## Lijian Yao
Your Lead Roles: Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 7 | 5 | 2 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 |  |  |  |  | 0.5 | 1 | 0.5 | 1.Set up git 2.Set up a team 3.communication plan 4.Meet teammates | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. | 1.Finishing up Algorithm within few week | 1. Learning 2. Finishing SPP doc 3.Prepare for Presentation | 7
2 | 09/14-09/21 | 7 | 5 | 2 | 0 - read several tutorials, choose the best tool to use for our team 5 - make project plan, received all the task assigned by team leader 6 - set up git, finishing up the SPPP doc 7 - Prepare presentation | 3 |  |  |  |  | 0.5 | 1 | 0.5 | 1.Finished SPPP doc 2.Prepare for presentation 3.Finishing up Algorithm | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet 2. communication is not clear. Task assignments is not clear. 3.We lost a Teammate so we had to fill in his role | 1.Finishing up Algorithm within few week | 1. Learning 2.Framework 3.Algorithm more TBD by next meeting | 7
3 | 09/21-09/28 | 7 | 5 | 2 | 0-learn algorithm part assigned by team leader 5-make sure everyone is doing their job so no duplicate work 6-learn how to use Pivotal Tracker 7-prepared for Lab2 | 3 |  |  |  |  | 0.5 | 1 | 0.5 | 1.Finished SPPP doc 2.Help Setting up Pivotal Tracker for every group members. 3.Finishing up Algorithm | 1.Almost everyone in our team only familar with backend so I am now the one who responsible for the UI. 2.Communiaction is getting better. | 1.Learning all the required things | 1.Learning 2.UI 3.communicating | 10
4 | 09/28- 10/05 | 12 | 10 | 2 | 0-learn how to create UI & HTML & paper 5-communicate with teammates for what UI page do we need 7-quiz | 8 |  |  |  |  | 1 |  | 1 | 1.Get UI pages design mindset sorted out 2.get all the learning done(UI) 3.Ask leader for things to do 4.Finished quiz | 1.Learning UI design and everything is new for me but I am kind of enjoying it | 1.Get the UI pages done 2.learning | 1.Learning 2.design UI pages 3.communicating | 14
5 | 10/05 - 10/12 | 20 | 18 | 2 | 0-learn how to create UI & HTML 2-design the UI pages 5 - asked group memeber what function they want in the UI pages and get the UI preview set up 7-perpared for presentation | 7 |  | 8 |  |  | 0.5 | 1 | 1.5 | 1.Get some UI page done 2.prepared for presentation 3.ready to submit iteration1 | 1.Spend too much time to make things perfect. | 1.Get more UI pages done 2.learning | 1.Learning 2.link up some UI pages 3.communicating | 15
6 | 10/12 - 10/19 | 20 | 18 | 2 | 0-learn how to create UI & HTML 2-design more UI pages 5 - asked group memeber what function they want in the UI pages and get the UI preview set up 7-review class material | 7 |  | 8 |  |  | 0.5 | 1 | 1.5 | 1.Get more UI page done 2.more learning 3.ready to submit iteration1 |  | 1.Get more UI pages done 2.learning | 1.Learning 2.link up some UI pages 3.communicating | 15
7 | 10/19 - 10/26 | 12 | 10 | 2 | 0-learn how to create UI & HTML&JS 2-design more UI pages, we have the final idea for the whole UI setups 5 - asked group memeber what function they want in the UI pages and get the UI preview set up 7-review class material | 5 |  | 3 |  |  | 0.5 |  | 1.5 | 1.Having every html page conceive 2.Redraw UI-Mock up to match the final idea UI setups 3. Learned more about coding JS | Wasn't able to attend group meeting but was able to had 1 on 1 meeting with groupleader to walk through it | 1.Finalized UI design 2.Getting more pages done. 3.Diging more about JS part | 1.Learning 2.Finalized UI pages design and possibly create a demo 3.communicating | 20
8 | 10/26 - 11/02 | 25 | 23 | 2 | 0-learn developing UI & HTML&JS 2-design more UI pages and having all the JS funtion runing on the page & creat a demo 5-Show my work to teammate during meeting 7-review class material | 8 |  | 8 | 5 |  | 1 |  | 1 | 1.Having every html page up and runing as a demo 2. Explained everything to teammates 3. Learned more about coding JS | Used to much time learning Javascript Had some miscommuncition with teammates did some unnesscary job | 1.Getting ready for persentation 2.Help connecting all my works to controller and handover works to teammates 3.Start learning Django | 1.Learning 2.Make some little changes 3.communicating | 15
9 | 11/02 - 11/09 | 12 | 10 | 2 | 0-learn developing UI & HTML & JS and Django 2-Make all the changes that required from teammate 5-learning about Django meeting 7-review class material | 6 |  | 3.5 |  |  | 0.5 | 1 | 1 | 1.Having every html page up and runing as a demo & made changes that needed. 2. Had communction with teammates about distribute work 3. Learned more about Django |  | 1.Submitting Iteration 1 2.Help connecting all my works to controller and handover works to teammates 3.learning Django | 1.Learning 2.Group work 3.communicating | 15
10 | 11/09 - 11/16 | 8 | 6 | 2 | 0-learn developing UI & HTML & JS and Django 2-Make all the changes that required from teammate 5-learning about Django during meeting 7-review class material | 3 |  | 1 |  |  | 0.5 | 1 | 0.5 | 1.Having every html page up and runing as a demo & made changes that needed. 2. Had communction with teammates about distribute work 3. Learned more about Django | to much time learning | 1.Help connecting all my works to controller and handover works to teammates 3.learning Django | 1.Learning 2.Group work 3.communicating | 12
11 | 11/16 - 11/23 | 10 | 8 | 2 | 0-learn developing UI & HTML & JS and Django 2-Make all the changes that required from teammate 3- Starting to connect UI pages 5-learning about Django during meeting 7-review class material | 3 |  | 1 | 2 |  | 0.5 | 1 | 0.5 | 1.Having every html page up and runing as a demo & made changes that needed. And connecting UI through Django. 2. Had communction with teammates about distribute work 3. Learned more about Django | to much time learning | 1.Help connecting all my works to controller and handover works to teammates 3.learning Django | 1.Learning 2.Group work 3.communicating | 12
12 | 11/23 - 11/30 | 12 | 10 | 2 | 0-learn developing UI & HTML & JS and Django 2-Make all the changes that required from teammate 3-Starting to connect UI pages 5-learning about Django during meeting 7-review class material | 3 |  | 1 | 4 |  | 0.5 | 1 | 0.5 | 1.Having every html page up and runing as a demo & made changes that needed.And connecting UI through Django. 2. Had communction with teammates about distribute work 3. Learned more about Django | communcation wasn't good | 1.Help connecting all my works to controller and handover works to teammates 3.learning Django | 1.Learning 2.Group work 3.communicating 4.Finishing everything up | 26
13 | 11/30 - 12/07 | 20 | 18 | 2 | 0-learn developing UI & HTML & JS and Django 2-Make all the changes that required from teammate 3-finishing UI 5-learning about Django during meeting 7-prepare for final presentation | 6 |  | 4 | 8 |  | 0.5 | 1 | 0.5 | 1.Having every html page up and runing as a demo & made changes that needed. And connected UI through Django. Finishing project 2. Had communction with teammates about distribute work 3. Learned more about Django |  |  | final

## Ruotong Wang
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 0 | 0 | 0 | Not Add this course | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
2 | 09/15-09/21 | 0 | 0 | 0 | Not Add this course | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
3 | 09/22-09/28 | 12 |  | 9 | 0 - read the resarch paper and search related feature 1 - divide the features in different part of class 2 - design user case and the class diagram 4 - find some security test function 5 - discuss the structure with teammates | 3 | 1 | 2 | 0 | 3 | 3 | 0 | 0 | 1. UML class diagram 2. User case | 1. The multiple choice objective score function in the paper is not fullfilled the instructor's requirement. 2. Need to learn Django | 1. Need to modify the origin objective function for calculating multiple choice question 2. Learn Djando | 1. Find a solution to calculate the multiple choices 2.Design Database | 5
4 | 09/29- 10/05 | 11 | 8 | 3 | 0 - read new paper: single choice question 2 - design class diagram 3 - database for group 5 - discuss about multiple choice | 3 | 0 | 1 | 4 | 0 | 3 | 0 | 0 | 1. Implement database design 2. Built classes | 1. The multiple choice objective score function in the paper is not fullfilled the instructor's requirement. | 1. find paper for multiple choice | 1. multiple choice question 2. architrcher design | 7
5 | 10/06 - 10/12 | 18 | 10 | 8 | 0 - learning for multiple choice 1 - divide system into three subsystem for different features 2 - design database 3 - database 5 - discuss about multiple choice | 4 | 2 | 1 | 3 | 0 | 8 | 0 | 0 | 1. Implemented architecture design 2. Graphed classs diagram | 1. Need to solve the self-defined weight from multiple choice | Try to change a algorithm to solve | 1. database design 2.feature divided 3.learnDjango | 9
6 | 10/13 - 10/19 | 20 | 16 | 4 | 0 - learning algorithm 2 - design class 3 - try to code multiple choice 5 - discuss swap and multiple choice | 3 | 0 | 3 | 10 | 0 | 4 | 0 | 0 | 1. Pesudocode for climbing hill algorithm 2. Created and modified the class correspondingly | 1. database incompatible | 1. divide system into three part for helping to understaing and assign task | 1. Implemented the pesudocode 2. Create tests to tests the functionality | 3
7 | 10/20 - 10/26 | 17 | 10 | 7 | 0 - learning Django 2 - design MVC in django 3 - Implment model in group branch / debug in model 5 - discuss MVC in Django | 4 | 0 | 3 | 4 | 0 | 7 | 0 | 0 | 1. Code model of group in Django 2. finished MVC part in SDD | 1. URL and page had some problem of page turns | 1. re-design page | 1. Implement user, survey, and instance controller | 6
8 | 10/27 - 11/3 | 27 | 22 | 5 | 0 - learning Django 2 - design URL in django 3 - Implment survey part(model, view(controller)) 4 - write login test in django 5 - discuss URL | 5 | 0 | 6 | 10 | 1 | 5 | 0 | 0 | 1. basic view functions for survey 2. implment the design of the URL | 1.URL and page had some problem of page turns 2. did not design all the need page before | 1. list URL and divide into different part according to subsystem | 1. Implement and integrate iGroup app to our main web application | 4
9 | 11/3 - 11/9 | 10 | 7 | 3 | 0 - learning test 3 - prepare for presetation 5 - discuss URL | 3 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 1. view in dajangp for survey 2. creat "import/export" | 1. need more convince way to upload | 1. creat new feature | 1. need import and export function for upload answer data 2.finish new branch "Export/Import" 3. learn test | 3
10 | 11/9 - 11/16 | 25 | 20 | 5 | 0 - learning Django 1 - requirement analysis : need import and export function for upload answer data 3 - finish new branch "Export/Import" 4 - import fuction test 5 - with team mate to use Django controllor to connect pages | 6 | 7 | 0 | 2 | 5 | 5 | 0 | 0 | 1 - requirement analysis : need import and export function for upload answer data 3 - finish new branch "Export/Import" 4 - import fuction test 5 - with team mate to use Django controllor to connect pages | 1. some bug in import fuction | 1. try to debug | 1. debug 2. check SDD SPPP | 7
11 | 11/16 - 11/23 | 14 | 11 | 3 | 0 - learning Django 3 - code controller(view) in Django 4 - some fuction test 5 - with team mate to use Django controllor to connect pages | 4 | 0 | 0 | 5 | 2 | 3 | 0 | 0 | 1. learning Django 2. code controller(view) in Django 3. some fuction test 4. with team mate to use Django controllor to connect pages | 1. have new bug when added some new feature | 1. debug 2. test | 1. debug 2. study security | 4
12 | 11/23 - 11/30 | 9 | 8 | 1 | 0 - learning Django and study test and security 3 - test report model 4 - test feature 5 - connect QA leader talk about test | 3 | 0 | 0 | 4 | 1 | 1 | 0 | 0 | 1. learning Django 2. some fuction test 3. write SDD STD | 1.bug | 1. prepare iteration 3 | 1. perpare
13 | 11/30 - 12/7 | 4 | 3 | 1 | 5 - discuss presetation 7 - Perpare Iteration3 | [5 empty] | 1 |  | 3 | finished | none | none | none

## Haiyang Wang
Your Lead Roles: QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/07-09/14 | 8 | 6 | 2 | 0 - learn git, github, github desktop, 1 - define high level requirements, 5 - make project plan, send reminders to team members, 6 - set up git, 7 - research similar products, prepare presentation. | 3 | 1 | null | null | null | 0.5 | 1 | 0.5 | 1.Bulid initial plan of project 2. Set up git, commit a test message on git 3. Participate in Iteration 0 | 1.Due to the late selection of the project topic, the algorithm and framework have not been designed yet, 2. communication is not clear. Task assignments is not clear. | 1. Communicate with teammates, frame design decided, 2. Task assignments successfully finished | 1. Reading References, 2. Finish Algorithum design | 6 - 12
2 | 09/15-09/21 | 10 | 7 | 3 | 0 - learn basic contents of testing, 1 - analysis the requirement for the iGroup project, 2 - reading literatures and design project algorithm, 5 - Make the final decision of each role together. 7- Finish sessions in SPPP, SPPP_RiskManagement | 3 | 1 | 3 | null | null | 0.5 | null | 2.5 | 1. Finish QA session in SPPP, finish testing and integration sessions in SPPP_RiskManagement, 2. Participate in Iteration 0 presentation | 1. Due to the late selection of the project topic, although the algorithm and framework have been designed, we still need consider about algorithm detail 2. leader role for team work is not clear | 1. finish Algorithm in 1 weeks, 2. Get the role, tasks finished | 1. Reading References, 2. Finish Algorithum design 3. Learn more about testing | 9 - 15
3 | 09/22-09/28 | 9 | 7 | 2 | 0 - learn algorithm, learn tests 5 - Coworking 6 - learn Pivotal Tracker 7- preparing Lab2 | 4 | null | null | null | null | 2 | 1 | 2 | 1. Modify SPPP 2. Setting Pivital Trakcer 3. Start to think about the basic of tests | 1. New on Pivotal Tracker | 1. Start learning it | 1. Reading 2. Learning tests concepts 3. lab 2 | 9 - 15
4 | 09/29- 10/05 | 10 | 8 | 2 | 0 - learn tests on python 1 - designing model of tests 5 - co working 7 - lab2 | 6 | 2 | null | null | null | 2 | null | null | 1. Design the frame of tests 2. Write some user story | 1. My user storirs have mistakes | 1. Modify the stories, problem solved | 1. Reading 2. Learning tests concepts 3. design model | 9 - 15
5 | 10/06 - 10/12 | 12 | 8 | 4 | 0 - learn tests on python 1 - designing model of tests 5 - talk about what should we do in the future 6 - set up git enviroment | 4 | 2 | null | null | null | 4 | 2 | null | 1. thinking about what should we test 2. Design test model | 1. Not all algorithms are finished, only start writing about obout other tests | 1. Waiting for complete | 1. Reading 2. Learning tests on python 3. Writing some test | 9 - 15
6 | 10/13 - 10/20 | 12 | 8 | 4 | 0 - learn tests on python 4 - write some tests about init 5 - talk about metrix and futurn tests 7 - modify SPPP | 2 | null | null | null | 4 | 4 | null | 2 | 1. Write some tests 2. Modify SPPP | 1. Not all algorithms are finished, only start writing about obout other tests | 1. Waiting for complete, write some tests first | 1. Reading 2. Continue to learn tests on python 3. Writing more test | 9 - 15
7 | 10/20 - 10/26 | 14 | 12 | 2 | 0 - learn tests on python 3 - modify source code 4 - write test_questions, test_surveys 5 - meeting | 4 | null | null | 2 | 6 | 2 | null | null | 1. write some tests | 1. some source code ignored special input like None | 1. modified code | 1. learning 2. Continue to write test | 10 - 15
8 | 10/27 - 11/2 | 14 | 12 | 2 | 0 - learn tests 3 - modify source code refactoring some code 4 - write test_answer, test_answer_sheets 5 - meeting | 2 |  |  | 4 | 6 | 2 |  |  | 1. write some tests 2. refactoring some parts of source code | 1. some source code ignored special input like None 2. There is a data type not clear, cannot figure out where it is list or dict | 1. modified code 2. that data should be list | 1. Continue to write test, finish tests in source_code/app | 10 - 15
9 | 11/3 - 11/9 | 18 | 12 | 2 | 0 - learn tests on python 3 - modify source code, refactoring 4 - write test_single_choice_score, test_multiple_choice_score, test_team 5 - meeting, talking about future process 7 - write STD | 2 |  |  | 4 | 6 | 2 |  | 4 | 1 . write some tests 2. fix conflict 3. refactoring some parts of code | 1. The data type mentioned last week should actually be a dict() | 1. fix errors and conflict, modify source code | 1. write some django tests | 10 - 20
10 | 11/10 - 11/16 | 10 | 8 | 2 | 1. analyze the performance of algorithm 4 - write test_weight 5 - meeting, talking about future process | 2 | 2 |  |  | 4 | 2 |  |  | 1. analyze the results of algorithm 2. decide the definision of perfect teams 3. write test | cannot decide whether or not to change a part of source code | wait for future testing | 1. find the needed rate of accuracy 2. write more tests | 8 - 12
11 | 11/17 - 11/23 | 10 | 8 | 2 | 1. analyze the performance of algorithm 4 - write test_mixed_question_weight 5 - meeting, talking about future process | 2 | 2 |  |  | 4 | 2 |  |  | 1. analyze the results of algorithm 2. decide the rate of accuracy 3. write test | test cases is not complicated enough | add more factors | 1. test more situations | 8 - 12
12 | 11/24 - 11/30 | 10 | 8 | 2 | 4 - write test_for_effects_of_more_choices, test_for_effects_of_more_questions 5 - meeting, talking about future process | 2 |  |  |  | 6 | 2 |  |  | 1. write tests | no sepecial issues |  |  | 8 - 12
13 | 12/01 - 12/10 | 10 | 8 | 2 | 4 - finish test_for_effects_of_more_quesitions, write test_for_effects_of_num_of_teams 7 - write STD | 2 |  |  |  | 4 | 2 |  | 2 | 1. write tests 2. finish documents | no sepecial issues